## Sheet1 (hidden)
İP No | İş Paketi Adı/Tanımı | SORUMLU
1 | KAVRAM GELİŞTİRME | İTÜ - TUSAŞ
1.1 | Literatür Araştırması ve Benzer Platform Özelliklerinin Belirlenmesi | İTÜ
1.2 | Mevcut Teknolojik Gelişimlerin İncelenmesi | İTÜ
1.3 | Hedef Pazarların Belirlenmesi | TUSAŞ
1.4 | Fizibilite Çalışması | TUSAŞ
2 | PLATFORM TASARIMI | İTÜ
2.1 | Ağırlık Tahmini | İTÜ
2.2 | Aerodinamik Analiz | İTÜ
2.3 | Konfigürasyon Seçimi | İTÜ
2.4 | Güç Grubu Seçimi ve Platform Entegrasyonu | İTÜ
2.5 | Taşıyıcı Yüzey Boyutlandırması | İTÜ
2.6 | Malzeme Seçimi | İTÜ
2.7 | Yapısal Analiz | İTÜ
2.8 | Aeroelastik Analiz | İTÜ
2.9 | Elektrik Sistemi Tasarımı | İTÜ
2.10 | Aviyonik Sistem Tasarımı | İTÜ
2.11 | Kokpit Tasarımı | İTÜ
2.12 | Üretim Teknikleri | İTÜ
2.13 | Performans, Stabilite ve Kontrol | İTÜ
3 | SİSTEM EMNİYETİ SAĞLAMASI | TUSAŞ - İTÜ
4 | UÇUŞ KONTROL SİSTEMİ | TUSAŞ
4.1 | Uçuş Kontrol Sistemi Tasarımı | TUSAŞ
5 | PROTOTİP İMALATI | TUSAŞ
5.1 | Yapısal İmalat | TUSAŞ
5.2 | Elektrik İmalat | TUSAŞ
5.3 | Elektronik İmalat | TUSAŞ
5.4 | Montaj | TUSAŞ
6 | TESTLER VE DOĞRULAMA | TUSAŞ - İTÜ
6.1 | Güç Grubu Testleri | TUSAŞ
6.2 | Yapı ve Malzeme Testleri | TUSAŞ - İTÜ
6.3 | Uçuş Görevi Testleri | TUSAŞ
6.4 | Test Sonuçlarının Değerlendirilmesi ve Optimizasyon Çalışması | TUSAŞ - İTÜ

## PUT_Detay
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | T0+: Concept Development Phase (3 Weeks)
2 | T0+: Assesment of System Requirement Phase (3 Week)
3 | T0+: Conceptual Design and Preliminary Design Phase (4 Weeks)
4 | T0+: Critical Design Phase (18 Weeks)
5 | T0+: Test & Evaluation Phase (19 Weeks)
6 | T0+: Implementation & Finalization Phase
7 | T0+: Project Ending (t0+28 Weeks)
1 | T0+: Concept Development Phase
1.1 | T0+: Activities
1.1.1 | T0+: Literature Research and Determinition and Similar Plartform Spesifications
1.1.2 | T0+: Feasibility Works
1.2 | T0+: Outcomes
2 | T0+: Sistem Gereksinimleri Değerlendirme Fazı
2.1 | T0+: Activities
2.1.1 | T0+: Üst Seviye Uçak Gereksinimlerinin Belirlenmesi
2.1.2 | T0+: Sistem Gereksinimlerinin Belirlenmesi
2.2 | T0+: Outcomes
2.2.1 | T0+: Bussiness Statement Report
3 | T0+: Conceptual Design and Preliminary Design Phase
3.1 | T0+: Activities
3.1.1
3.1.2
3.1.3
3.1.4
3.1.5
3.1.6
3.1.7
3.1.8
3.1.9
3.1.10
3.2 | T0+: Outcomes
3.2.1 | T0+: Preliminary Report
4 | T0+: Critical Design Phase
4.1 | T0+: First Semester
4.1.1
4.1.2
4.1.3
4.1.4
4.1.5
4.1.6
4.1.7
4.1.8
4.1.9
4.1.10
4.2 | T0+: First Semester Outcomes
4.2.1 | T0+: Standarts Report
4.2.2 | T0+: Module Test Demo
4.2.3 | T0+: Conceptual Design Report
4.2.4 | T0+: Presentations
4.3 | T0+: Second Semster
4.3.1
4.3.2
4.3.3
4.3.4
4.3.5
4.3.6
4.3.7
4.3.8
4.3.9
4.3.10
4.4 | T0+: Second Semester Outcomes
4.4.1 | T0+: Critical Design Review Report
5 | T0+: Test & Evalution Phase
5.1 | T0+: First Semester Activities
5.1.1
5.1.2
5.1.3
5.1.4
5.1.5
5.1.6
5.1.7
5.1.8
5.1.9
5.1.10
5.2 | T0+: First Semester Outcomes
5.2.1
5.2.2
5.2.3
5.2.4
5.3 | T0+: Second Semester Activities
5.3.1
5.3.2
5.3.3
5.3.4
5.3.5
5.3.6
5.3.7
5.3.8
5.3.9
5.3.10
5.4 | T0+: Second Semester Outcomes
5.4.1 | T0+: Critical Design Review Report
6 | T0+: Finalization Phase
6.1 | T0+: Activities
6.1.1
6.1.2
6.1.3
6.1.4
6.1.5
6.1.6
6.1.7
6.1.8
6.1.9
6.1.10
6.2 | T0+: Outcomes
6.2.1 | T0+: Finalized Product
6.2.2 | T0+: Final Report
6.2.3 | T0+: Final Demo
7 | T0+: Project Ending

## PUT_Detay (2)
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | T0+: Concept Development Phase (3 Weeks)
2 | T0+: Assessment of System Requirement Phase (3 Week)
3 | T0+: Conceptual Design and Preliminary Design Phase (4 Weeks)
4 | T0+: Critical Design Phase (18 Weeks)
5 | T0+: Test & Evaluation Phase (19 Weeks)
6 | T0+: Implementation & Finalization Phase
7 | T0+: Project Ending (t0+28 Weeks)
1 | T0+: Concept Development Phase
1.1 | T0+: Activities
1.1.1 | T0+: Literature Research and Determinition and Similar Platform Specifications
1.1.2 | T0+: Feasibility Works
2 | T0+: Assessment of System Requirement Phase
2.1 | T0+: Activities
2.1.1 | T0+: Determination of Team Logo and Vision&Mission
2.1.2 | T0+: Problem Define State for All Projects
2.1.3 | T0+: Solve Defined Problem State for All Projects
2.1.4 | T0+: General Component Research
2.2 | T0+: Outcomes
2.2.1 | T0+: Business Statement Report
3 | T0+: Conceptual Design and Preliminary Design Phase
3.1 | T0+: Activities
3.1.1 | T0+: Preliminary Electrical System Design
3.1.1.1 | T0+: Preliminary Sensing Unit Design
3.1.1.2 | T0+: Preliminary Computational Unit Design
3.1.1.3 | T0+: Preliminary Driving Unit Design
3.1.2 | T0+: Preliminary Mechanical System Design
3.1.2.1 | T0+: Preliminary Motion Unit Design
3.1.2.2 | T0+: Preliminary Structure Design
3.2 | T0+: Outcomes
3.2.1 | T0+: Preliminary Report
4 | T0+: Critical Design Phase
4.1 | T0+: First Semester
4.1.1 | T0+: Electrical System Design
4.1.1.1 | T0+: Sensing Unit Design
4.1.1.2 | T0+: Computational Unit Design
4.1.1.3 | T0+: Driving Unit Design
4.1.2 | T0+: Mechanical System Design
4.1.2.1 | T0+: Motion Unit Design
4.1.2.2 | T0+: Structure Design
4.1.3 | T0+: To be detailed
4.2 | T0+: First Semester Outcomes
4.2.1 | T0+: Standards Report
4.2.2 | T0+: Module Test Demo
4.2.3 | T0+: Conceptual Design Report
4.2.4 | T0+: Presentations
4.3 | T0+: Second Semester
4.3.1 | T0+: To be detailed
4.4 | T0+: Second Semester Outcomes
4.4.1 | T0+: Critical Design Review Report
5 | T0+: Test & Evalution Phase
5.1 | T0+: First Semester Activities
5.1.1 | T0+: To be detailed
5.2 | T0+: First Semester Outcomes
5.2.1 | T0+: To be detailed
5.3 | T0+: Second Semester Activities
5.3.1 | T0+: To be detailed
5.4 | T0+: Second Semester Outcomes
5.4.1 | T0+: Critical Design Review Report
6 | T0+: Finalization Phase
6.1 | T0+: Activities
6.1.1 | T0+: To be detailed
6.2 | T0+: Outcomes
6.2.1 | T0+: Finalized Product
6.2.2 | T0+: Final Report
6.2.3 | T0+: Final Demo
7 | T0+: Project Ending

## PUT_Detay (3)
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | T0+: Concept Development Phase (3 Weeks)
2 | T0+: Assessment of System Requirement Phase (3 Week)
3 | T0+: Conceptual Design and Preliminary Design Phase (4 Weeks)
4 | T0+: Critical Design Phase (18 Weeks)
5 | T0+: Test & Evaluation Phase (19 Weeks)
6 | T0+: Implementation & Finalization Phase
7 | T0+: Project Ending (T0+28 Weeks)
1 | T0+: Concept Development Phase
1.1 | T0+: Activities
1.1.1 | T0+: Literature Research and Determination and Similar Platform Specifications
1.1.2 | T0+: Feasibility Works
2 | T0+: Assessment of System Requirement Phase
2.1 | T0+: Activities
2.1.1 | T0+: Determination of Team Logo and Vision & Mission
2.1.2 | T0+: Problem Define State for All Projects
2.1.3 | T0+: Solve Defined Problem State for All Projects
2.1.4 | T0+: General Component Research
2.2 | T0+: Outcomes
2.2.1 | T0+: Business Statement Report
3 | T0+: Conceptual Design and Preliminary Design Phase
3.1 | T0+: Activities
3.1.1 | T0+: Preliminary Electrical System Design
3.1.1.1 | T0+: Preliminary Sensing Unit Design
3.1.1.2 | T0+: Preliminary Computational Unit Design
3.1.1.3 | T0+: Preliminary Driving Unit Design
3.1.2 | T0+: Preliminary Mechanical System Design
3.1.2.1 | T0+: Preliminary Motion Unit Design
3.1.2.2 | T0+: Preliminary Structure Design
3.2 | T0+: Outcomes
3.2.1 | T0+: Preliminary Report
4 | T0+: Critical Design Phase
4.1 | T0+: First Semester
4.1.1 | T0+: Electrical System Design
4.1.1.1 | T0+: Sensing Unit Design
4.1.1.2 | T0+: Computational Unit Design
4.1.1.3 | T0+: Driving Unit Design
4.1.2 | T0+: Mechanical System Design
4.1.2.1 | T0+: Motion Unit Design
4.1.2.2 | T0+: Structure Design
4.1.3 | T0+: To be detailed
4.2 | T0+: First Semester Outcomes
4.2.1 | T0+: Standards Report
4.2.2 | T0+: Module Test Demo
4.2.3 | T0+: Conceptual Design Report
4.2.4 | T0+: Presentations
4.3 | T0+: Second Semester
4.3.1 | T0+: To be detailed
4.4 | T0+: Second Semester Outcomes
4.4.1 | T0+: Critical Design Review Report
5 | T0+: Test & Evalution Phase
5.1 | T0+: First Semester Activities
5.1.1 | T0+: To be detailed
5.2 | T0+: First Semester Outcomes
5.2.1 | T0+: To be detailed
5.3 | T0+: Second Semester Activities
5.3.1 | T0+: To be detailed
5.4 | T0+: Second Semester Outcomes
5.4.1 | T0+: Critical Design Review Report
6 | T0+: Finalization Phase
6.1 | T0+: Activities
6.1.1 | T0+: To be detailed
6.2 | T0+: Outcomes
6.2.1 | T0+: Finalized Product
6.2.2 | T0+: Final Report
6.2.3 | T0+: Final Demo
7 | T0+: Project Ending

## PUT_Detay (4)
|  | October 1-5 | October 8-12 | October 15-19 | October 22-26 | Oct 29 - Nov 02 | November 05-09 | November 12-16 | November 19-23 | November 26-30 | December 03-07 | December 10-14 | December 17-21 | December 24-28 | Dec 31 - Jan 04 | January 7-11 | January 14-18 | January 21-25 | January 28-31 | February 4-7 | February 11-14 | February 18-21 | February 25-28 | March 4-7 | March 11-14 | March 18-21 | March 25-28 | April 1-4 | April 8-11 | April 15-18 | April 22-25 | Apr 22 - May 05 | May 09-12 | May 12-15
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
1. Semester
Holiday
2. Semester
1 | T0+: Concept Development Phase (3 Weeks)
2 | T0+: Assessment of System Requirement Phase (3 Week)
3 | T0+: Conceptual Design and Preliminary Design Phase (4 Weeks)
4 | T0+: Critical Design Phase (17 Weeks)
5 | T0+: Test & Evaluation Phase (20 Weeks)
6 | T0+: Implementation & Finalization Phase (8 Weeks)
7 | T0+: Project Ending (T0+33 Weeks)
1 | T0+: Concept Development Phase
1.1 | T0+: Activities
1.1.1 | T0+: Literature Research and Determination and Similar Platform Specifications
1.1.2 | T0+: Feasibility Works
2 | T0+: Assessment of System Requirement Phase
2.1 | T0+: Activities
2.1.1 | T0+: Determination of Team Logo and Vision & Mission
2.1.2 | T0+: Problem Define State for All Projects
2.1.3 | T0+: Solve Defined Problem State for All Projects
2.1.4 | T0+: General Component Research
2.2 | T0+: Outcomes
2.2.1 | T0+: Business Statement Report
3 | T0+: Conceptual Design and Preliminary Design Phase
3.1 | T0+: Activities
3.1.1 | T0+: Preliminary Electrical System Design
3.1.1.1 | T0+: Preliminary Sensing Unit Design
3.1.1.2 | T0+: Preliminary Computational Unit Design
3.1.1.3 | T0+: Preliminary Driving Unit Design
3.1.2 | T0+: Preliminary Mechanical System Design
3.1.2.1 | T0+: Preliminary Motion Unit Design
3.1.2.2 | T0+: Preliminary Structure Design
3.2 | T0+: Outcomes
3.2.1 | T0+: Preliminary Report
|  | October 1-5 | October 8-12 | October 15-19 | October 22-26 | Oct 29 - Nov 02 | November 05-09 | November 12-16 | November 19-23 | November 26-30 | December 03-07 | December 10-14 | December 17-21 | December 24-28 | Dec 31 - Jan 04 | January 7-11 | January 14-18 | January 21-25 | January 28-31 | February 4-7 | February 11-14 | February 18-21 | February 25-28 | March 4-7 | March 11-14 | March 18-21 | March 25-28 | April 1-4 | April 8-11 | April 15-18 | April 22-25 | Apr 22 - May 05 | May 09-12 | May 12-15
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
4 | T0+: Critical Design Phase
4.1 | T0+: Subsystem Design Phase
4.1.1 | T0+: Sensing System Desing
4.1.1.1 | T0+: Lane Detection Subsystem Design
4.1.1.2 | T0+: Vehicle Detection Subsystem Design
4.1.2 | T0+: Computation System Desing
4.1.2.1 | T0+: Data Proccesing Subsystem Design
4.1.2.2 | T0+: PID Controller Subsystem Design
4.1.3 | T0+: Communication System Design
4.1.3.1 | T0+: Internal Communication Subsystem Design
4.1.3.2 | T0+: External Communication Subsystem Design
4.1.4 | T0+: Driving System Design
4.1.4.1 | T0+: Direction Subsystem Design
4.1.4.2 | T0+: Speed Subsystem Design
4.1.5 | T0+: Structure System Design
4.1.5.1 | T0+: Chassis Subsystem Design
4.1.5.2 | T0+: PCB Subsystem Design
4.1.6 | T0+: Motion System Design
4.1.6.1 | T0+: Wheels Subsystem Design
4.1.6.2 | T0+: Motors Subsystem Design
4.2 | T0+: Critical Design Outputs
4.2.1 | T0+: Standards Report
4.2.2 | T0+: Module Test Demo
4.2.3 | T0+: Conceptual Design Report
4.2.4 | T0+: Presentations
4.4.1 | T0+: Critical Design Review Report
|  | October 1-5 | October 8-12 | October 15-19 | October 22-26 | Oct 29 - Nov 02 | November 05-09 | November 12-16 | November 19-23 | November 26-30 | December 03-07 | December 10-14 | December 17-21 | December 24-28 | Dec 31 - Jan 04 | January 7-11 | January 14-18 | January 21-25 | January 28-31 | February 4-7 | February 11-14 | February 18-21 | February 25-28 | March 4-7 | March 11-14 | March 18-21 | March 25-28 | April 1-4 | April 8-11 | April 15-18 | April 22-25 | Apr 22 - May 05 | May 09-12 | May 12-15
5 | T0+: Test & Evalution Phase
4.1 | T0+: Subsystem Test Phase
4.1.1 | T0+: Sensing System Testing
4.1.1.1 | T0+: Lane Detection Subsystem Testing
4.1.1.2 | T0+: Vehicle Detection Subsystem Testing
4.1.2 | T0+: Computation System Testing
4.1.2.1 | T0+: Data Proccesing Subsystem Testing
4.1.2.2 | T0+: PID Controller Subsystem Testing
4.1.3 | T0+: Communication System Testing
4.1.3.1 | T0+: Internal Communication Subsystem Testing
4.1.3.2 | T0+: External Communication Subsystem Testing
4.1.4 | T0+: Driving System Testing
4.1.4.1 | T0+: Direction Subsystem Testing
4.1.4.2 | T0+: Speed Subsystem Design
4.1.5 | T0+: Structure System Testing
4.1.5.1 | T0+: Chassis Subsystem Testing
4.1.5.2 | T0+: PCB Subsystem Testing
4.1.6 | T0+: Motion System Testing
4.1.6.1 | T0+: Wheels Subsystem Testing
4.1.6.2 | T0+: Motors Subsystem Testing
6 | T0+: Finalization Phase
6.1 | T0+: Activities
6.1.1 | T0+: To be detailed
6.2 | T0+: Outcomes
6.2.1 | T0+: Finalized Product
6.2.2 | T0+: Final Report
6.2.3 | T0+: Final Demo
7 | T0+: Project Ending

## PUT_Detay (5)
|  | October 1-5 | October 8-12 | October 15-19 | October 22-26 | Oct 29 - Nov 02 | November 05-09 | November 12-16 | November 19-23 | November 26-30 | December 03-07 | December 10-14 | December 17-21 | December 24-28 | Dec 31 - Jan 04 | January 7-11 | January 14-18 | January 21-25 | January 28-31 | February 4-7 | February 11-14 | February 18-21 | February 25-28 | March 4-7 | March 11-14 | March 18-21 | March 25-28 | April 1-4 | April 8-11 | April 15-18 | April 22-25 | Apr 22 - May 05 | May 09-12 | May 12-15
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
1. Semester
Holiday
2. Semester
1 | T0+: Concept Development Phase
2 | T0+: Assessment of System Requirement Phase
3 | T0+: Conceptual Design and Preliminary Design Phase
4 | T0+: Critical Design Phase
5 | T0+: Test & Evalution Phase
6 | T0+: Finalization Phase
7 | T0+: Project Ending

## PUT_Detay (6)
|  | October 1-5 | October 8-12 | October 15-19 | October 22-26 | Oct 29 - Nov 02 | November 05-09 | November 12-16 | November 19-23 | November 26-30 | December 03-07 | December 10-14 | December 17-21 | December 24-28 | Dec 31 - Jan 04 | January 7-11 | January 14-18 | January 21-25 | January 28-31 | February 4-7 | February 11-14 | February 18-21 | February 25-28 | March 4-7 | March 11-14 | March 18-21 | March 25-28 | April 1-4 | April 8-11 | April 15-18 | April 22-25 | Apr 22 - May 05 | May 09-12 | May 12-15
| T0+ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
1. Semester
Holiday
2. Semester
1 | T0+: Moving on a Defined Path
2 | T0+: Detecting Lanes using Camera
3 | T0+: Integrate Camera Vision to Vehicle
4 | T0+: Following the Path with Camera Vision
5 | T0+: Implementation of Handshake in Software
6 | T0+: Implementation of Handshake in Hardware
7 | T0+: Realization of PID Parameters
8 | T0+: Implementation of all systems
9 | T0+: Testing of All Systems
10 | T0+: Project Ending

## Sheet1 (2) (hidden)
İP No | İP Adı/Tanımı | SORUMLU | KOORDİNATÖR
|  |  | ALTINAY | İTÜ
|  |  | ALTINAY | Metin Orhan KAYA
1 | KAVRAM GELİŞTİRME | İTÜ - TUSAŞ | ALTINAY | M. Adil YÜKSELEN
1.1 | Literatür Araştırması ve Benzer Platform Özelliklerinin Belirlenmesi | İTÜ |  | Hayri ACAR
1.2 | Mevcut Teknolojik Gelişimlerin İncelenmesi | İTÜ | ALTINAY | Halit S. TÜRKMEN
1.3 | Hedef Pazarların Belirlenmesi | TUSAŞ | ALTINAY
1.4 | Fizibilite Çalışması | TUSAŞ | ALTINAY
2 | PLATFORM TASARIMI | İTÜ - ALTINAY | ALTINAY | Metin Orhan KAYA
2.1 | Ağırlık Tahmini | İTÜ |  | Hayri ACAR
2.2 | Aerodinamik Analiz | İTÜ |  | M. Adil YÜKSELEN
2.3 | Konfigürasyon Seçimi | İTÜ |  | Hayri ACAR
2.4 | Güç Grubu Seçimi ve Platform Entegrasyonu | ALTINAY | ALTINAY
2.5 | Taşıyıcı Yüzey Boyutlandırması | İTÜ |  | M. Adil YÜKSELEN
2.6 | Malzeme Seçimi | İTÜ |  | Özge ÖZDEMİR
2.7 | Yapısal Analiz | İTÜ |  | Zahit MECİTOĞLU
2.8 | Aeroelastik Analiz | İTÜ |  | Metin Orhan KAYA
2.9 | Üretim Teknikleri | İTÜ |  | Halit S. TÜRKMEN
2.10 | Performans, Stabilite ve Kontrol | İTÜ |  | Hayri ACAR
2.11 | Meteorolojik veAtmosferik Yönetim | İTÜ |  | Ahmet D. ŞAHİN
3 | ENERJİ YÖNETİMİ | ALTINAY - İTü | ALTINAY | Vedat Z. DOĞAN
3.1 | Güneş Hücresi Araştırması ve Seçimi | ALTINAY | ALTINAY
3.2 | Teknolojisi Araştırması ve Seçimi | ALTINAY | ALTINAY
3.3 | Enerji Bileşenlerinin Platform İle Entegrasyonu | ALTINAY | ALTINAY
4 | OTOPİLOT ve KONTROL SİSTEMİ TASARIMI | ALTINAY - İTÜ | ALTINAY | Metin Orhan KAYA
4.1 | Uçuş Kontrol Algoritması | ALTINAY | ALTINAY
4.2 | Otopilot Sistemi Yazılımı ve Platform İle Entagrasyonu | ALTINAY | ALTINAY
4.3 | Kararlılık Destek Sistemi Yazılımı ve Platform İle Entegrasyonu | ALTINAY | ALTINAY
5 | PROTOTİP İMALATI | ALTINAY - İTÜ | ALTINAY | Halit S. TÜRKMEN
5.1 | Yapısal İmalat | ALTINAY | ALTINAY
5.2 | Elektrik İmalat | ALTINAY | ALTINAY
5.3 | Elektronik İmalat | ALTINAY | ALTINAY
5.4 | Yazılımın Devreye Alınması | ALTINAY | ALTINAY
5.5 | Montaj | ALTINAY | ALTINAY
6 | TESTLER VE DOĞRULAMA | ALTINAY - İTÜ | ALTINAY | İTÜ GRUBU
6.1 | Pil Testleri | ALTINAY | ALTINAY
6.2 | Güneş Pili Testleri | ALTINAY | ALTINAY
6.3 | Güç Grubu Testleri | ALTINAY - İTÜ | ALTINAY | Hayri ACAR
6.4 | Yapı ve Malzeme Testleri | İTÜ - ALTINAY | ALTINAY | Zahit MECİTOĞLU
6.5 | Uçuş Görevi Testleri | ALTINAY - İTÜ | ALTINAY | M. Adil YÜKSELEN
6.6 | Test Sonuçlarının Değerlendirilmesi ve Optimizasyon Çalışması | İTÜ - ALTINAY | ALTINAY | İTÜ GRUBU